## Sheet1
Item | P | I | Risk (P*I) | Recognized | Mitigated/ Resolved | ROAM | How
Incorrect Task Flow Assumptions | 13 | 40 | 520 | 2022-03-09 |  | O | Will conduct a review over the weekend
Falling Behind | 20 | 100 | 2000 | 2022-04-01 |  | O | Got organized in terms of planning when work needs to be get done and when to work on them. Rework Project Plans.
Incorrect usage of MutEx's and ITC | 13 | 8 | 104 | 2022-03-09 | Mitigated | M | Will review MutEx documentation
Incorrect Organization of Project Files | 2 | 8 | 16 | 2022-04-01 |  | R | Reviewed previous project work and Micrium docs
Testing Plan Fails to account for design conditions | 13 | 40 | 520 | 2022-03-17 |  | O | Be on the lookout when implementing code and tests for unaccounted factors
0
0
0
0

## Sheet2
Valid Modified Fibonacci values
1
2
3
5
8
13
20
40
70
100